## Timeline Template 0409
Implementation Timeline Template 1 |  |  | Feel free to use our template, edit this to fit your timeline needs, or create a new version. We also welcome clear handwritten drawnings. There are a few more templates on the subsequent sheets.
Project Name: | Cultural Harvest
Project Milestone | Tasks | Timeframe | Estimated Completion Date | Owner | Notes
Team Recruitment | Hiring and Identify SAB members interest on working on project, Kick off and role assigning | Jun - Jul | 2025-07-31 | CIRCLE SAB Chair(s), CIRCLE staff
Project Publication | Social media content design and publish | Sept - May'26 | 2025-05-31 | Outreach Coordinator | Using CIRCLE's channels as their profile already have numbers of followers
| Website Design and Publish | Sept | 2025-09-30 | Outreach Coordinator | Student lead
| Website content publish | Sept - May'26 | 2026-05-31 | Outreach Coordinator
| Poster design and hanging | Sept - May'26 | 2026-05-31 | Outreach Coordinator | Poster will be printed in recycle papers and use design that are sustainable friendly (using lighter fonts, minimize color block and the use of images, using draft mode)
| Reach out to the RSOs focuses on diversity | Sept - May'26 | 2026-05-31 | Outreach Coordinator | To gather preliminary interest
| Open Calling for Interest Students and evaluating | Oct - Nov | 2025-11-30 | Project Manager, CIRCLE SAB Chair(s), CIRCLE staff | Interest form: Short paragraphs on the cultural foods and their storytelling ideas. Evaluates: to categorize each storytelling tools and look into the accessibility issue that the project can possibly clear up (i.e partner with STF if there are student that willing to use videography/camera, provide art supply, etc)
| Administration | Sept - May'26 | 2026-05-31 | Project Manager, CIRCLE SAB Chair(s), CIRCLE staff | Cash flow, report, evaluation, communication across CIRCLE and UW (GPSS, ASUW, other SAB)
Partnership | Identify and confirm Panelist | Nov-Dec | 2025-12-31 | Project Manager, CIRCLE SAB Chair(s), CIRCLE staff
| Space reservation | Dec | 2025-12-31 | Project Manager
Events | Educational Workshop 1 | January | 2026-01-31 | Project Manager | Theme: Food, Nutrition, Culture
| Educational Workshop 2 | February | 2026-02-28 | Project Manager | Theme: Creative Communication Strategies
| Submission Open | Feb | 2026-02-28 | Project Manager, CIRCLE SAB Chair(s), CIRCLE staff
| Submission Deadline | April | 2026-04-10 | Project Manager, CIRCLE SAB Chair(s), CIRCLE staff
| Submission evaluation and votes | April - May | 2026-05-10 | Project Manager, CIRCLE SAB Chair(s), CIRCLE staff
| UW Cultural Harvest Day Celebration | May | 2026-05-21 | Project Manager, CIRCLE SAB
Project Closing | Transfer to CIRCLE Website | Sept | 2026-09-30 | CIRCLE Staff | Ensure that all content will still accessible aftr the funding period ended.