## Timeline Template 3
Implementation Timeline Template 3
Project Name: | Project Indoor Farming
Project Element | Task | Sub Task | Owner | Notes | 2025
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Hand Washing Sink | Set up process | Farm Manager | bar: 2025 Sept
| Keypad for Door | Communicate with UW Facilities | Farm Manager | bar: 2025 July
Health and Safety
| Computer System | Configure systems | Technology Manager | bar: 2025 June
| Pumps | Attach to system | Farm Manager | bar: 2025 Sept
Technology