## Sheet1
Implementation Timeline
Project Name: | Glass Art Energy: The Future of Glass Art Making
Project Milestone | Tasks | Timeframe | Notes
| Gather Information | December | Utilize information gathered from Undergraduate Research Project and continue to research topics
| Organize Information | January | Compile information into comprehensive categories such as scope, technologies, and implimentation
PHASE ONE: Establish website | Content Creation | February | Create graphics, powerpoints, and other user-friendly content for outreach
| Website Design | 2026-02-10 | Design accesible, user-friendly website. Soft launch date of 2/10/2026
| Peer-review | Late February | Conduct Peer-review groups to verify and collaborate about information topics and categories.
PHASE TWO: | Outreach Seminar | March | Outreach Seminar, open to the public. Powerpoint presentation and interactive lecture about ways to be more energy effient in your studios.
Outreach
PHASE THREE: | Incorporate into ciriculum | April | Incorpoarate educational information into ciriculum for my ART233 Intro to Glass class in the Spring Quarter
Implementation