## Timeline Template 1
Implementation Timeline Template 1 |  |  | Feel free to use our template, edit this to fit your timeline needs, or create a new version. We also welcome clear handwritten drawnings. There are a few more templates on the subsequent sheets.
Project Name: | The Khmer New Year Show
Project Milestone | Tasks | Timeframe | Estimated Completion Date | Owner | Notes
| Dance Practices | January - May | 2025-05-03 | Trot and Coconut and Blessing Teams
| Skit Practices | Febuary - May | 2025-05-03 | Skit Team
Outreach / Promo | Promotional Flyers | Febuary - March | 2025-02-26 | Media
Outreach / Promo | Promotional Video | March - April | 2025-04-01 | Media
| Collect Raffle Items | March - April | 2025-04-18
| Get Voulnteers | April - May | 2025-05-03
| Begin Selling Tickets | March 1st - May 3rd | 2025-05-03 | KHSA | Paper Tickets: 500 - 550 (UW Student/Staff 180 and General 320)

## Timeline Template 2
Implementation Timeline Template 2
Project Name:
Project Element | Task | Owner | Notes | Deadlines (quarter based)
|  |  |  | Summer 24 | Autumn 24 W3 | Autumn 24 W7 | Winter 25 W4 | Winter 25 W8 | Spring 25 W1 | Summer 25
| Retrofit Permissions | Fotima
| Design Plan | Kyle
PACCAR Skybridge | Installation | Yahia
| Monitoring Begins | Rasheena
| Live Bird Screens | Gulsima

## Timeline Template 3
Implementation Timeline Template 3
Project Name:
Project Element | Task | Sub Task | Owner | Notes | 2024 | [11 empty] | 2025
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Design | Blueprint | Boe | bar: 2024 Jan
| Implementation | Ground prep | Tatiana | bar: 2024 March
Storage Facility |  | Purchase materials | Kort | bar: 2024 June
|  | Construction | Danny | bar: 2024 June