## Sheet1
Timeframe | Task | Notes
1 Year Prior (The Previous June) | Reserving Red Square | Reserving the space required for the event itself
Fall Quarter | Reserving Kitchen Space | Reserving space required for our food booth preparation
Fall Quarter - Spring Quarter | Funding Applications | Fundraising for event expenses and sponsorships
Winter Quarter- Spring Quarter | Vendor Contracts | Signing agreements with our vendors and partners
Winter Quarter - Spring Quarter | Marketing Campaign Begins | Our marketing for the event begins + outreach for our intiatives and policies
Winter Quarter - Spring Quarter | Facilities Rentals | Securing tents, sound equipment, honey buckets, generators, and parking for our event
Winter Quarter | Food Booth Testing | The process of testing our kitchen equipment as well as Day of bandwidth
Spring Quarter | Menu Finalization | Choosing the final menu items we will be serving Day of at the event
Spring Quarter | Entertainment Contracts | Signing contracts and agreements with our performers throughout the event
Spring Quarter | Performance Finalization | Organizing the entertainment schedule as well as sound equipment needed
Day of | Day Before Kitchen Preparation | Preparation of the food needing to be served the next day to the over 7,000 attendees
Day of | Day Of Preparation | Loading in security, tenting, vendors, food booths, performers, and various other equipments