## PETS Timeline
Implementation Timeline
Project Name: | PETS
Project Element | Task | Sub Task | Owner | Notes | 2025 | [11 empty] | 2026
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Order Parts |  | Mia | bar: 2025 Jan to 2025 Oct
| Implementation | Coordination | Noah
Hardware |  | Solar Panel & Blocks | Mia | bar: 2025 Nov
|  | Electronic System Safety Tests | Noah | bar: 2025 Dec to 2026 Jan
Sensors | bar: 2026 Jan
| Additions | Coordination | Noah
|  | Debug Sensor Drift | Christoff | bar: 2026 March to 2026 May
|  | Experiment with remote load | Noah | bar: 2026 March to 2026 May
| Build Software Plan |  | Anika | bar: 2025 Oct to 2025 Dec
| Workshops with RTU Expert |  | Anika | bar: 2025 Dec
Software | Graphana Server Access |  | Anika | bar: 2025 Dec
| V1 of Datalogger |  | Noah | Bare bones | bar: 2026 Jan to 2026 Feb
| V2 of Datalogger |  | Noah | Presentable open-access website | bar: 2026 April to 2026 May
Noa
| Find Funding Sources |  | Noah | bar: 2025 July to 2025 Oct
| Create Documentation |  | Noah | bar: 2026 Jan to 2026 April
Outreach | RSO collaborations |  | Maddie | Info and Solar orgs like UW solar and WINFO | bar: 2026 Feb to 2026 June
| Publish on Medium Articles |  | Maddie | bar: 2026 Feb to 2026 March; 2026 Sept to 2026 Oct