## Timeline Template 1
Implementation Timeline Template
Project Name: | Community Design Building Rain Garden Yard Revitalization
Project Milestone | Tasks | Timeframe | Estimated Completion Date | Owner | Notes
Summer Quarter
Garden Design and Planting | Clear existing planting beds | Late May-Early June | 2025-06-13 | Nicole, Emma, student volunteers | This volunteer service will be completed by graduate student volunteers who are already identified and committed to the project
Garden Design and Planting | Develop Phase 1 planting design: native annuals | Mid-June | June 10th and 12th | Nicole, Emma, student volunteers | This volunteer service will be completed by graduate student volunteers, with guidance from Katie Kadwell and the Landscape Architecture department
Garden Design and Planting | Phase 1 planting implementation | June | June 17th and 19th | Nicole, Emma, student volunteers | This volunteer service will be completed by graduate student volunteers who are already identified and committed to the project
Garden Design and Planting | Phase 1 planting maintenance | June-September | Seasonal, as needed | Nicole, Emma, student volunteers | This volunteer service will be completed by graduate student volunteers who are already identified and committed to the project
Garden Design and Planting | Recruiting for ongoing planting implementation and maintenance volunteers | June-September | Start of fall quarter | Nicole, Emma | Communication through existing UW student groups and departments to identify and recruit volunteers for ongoing maintenance and planting volunteer work
Garden Design and Planting | Confirm volunteers and send fall quarter schedule | September | Start of fall quarter | Nicole, Emma
Community Design Charrette | Begin stakeholder conversations with UW staff to determine design/build constraints for stormwater collection tank | Summer and fall quarters | Mid-winter quarter at latest | Nicole, Emma, Jim | This stakeholder process has the potential to significantly affect the subsequent timeline. We understand that our design and build process will be contingent on the necessary UW stakeholder approval processes.
Community Design Charrette | Begin recruiting for design charrette participants | Late May-July | 2025-07-31 | Nicole, Emma | Communication through existing UW student groups, outreach to surrounding student housing, and outreach through UW networks (student newspapers etc)
Community Design Charrette | Confirm participants and send charrette schedule | July | July 31 2025 | Nicole, Emma | Communication via email
Community Design Charrette | Community design charrettes | August | August 5th, 7th, 9th | Nicole, Emma, Jim | 3, 3-hour charrettes, free and open to the UW community. Goal is to quickly iterate on sculptural rainwater capture and storage designs; introduce non-designers to process
Community Design Charrette | Begin recruiting for sculpture construction participants and maintenance volunteers | Start of fall quarter | August | Nicole, Emma | Communication through existing UW student groups and departments, plus existing planting volunteers and community design charrette participants, to identify and recruit volunteers for ongoing maintenance
| Present refined rainwater sculpture design to UW stakeholders | August | August 15th | Nicole, Emma, Jim | Begin review, ammendment and approval process for rainwater sculpture with Design Review Board and/or other UW stakeholders as necessary
| Integrate stakeholder feedback toward final design | fall quarter | September 30th | Nicole, Emma, Jim
Fall quarter
Garden Design and Planting | Develop Phase 2 planting design, native perennials | fall quarter | October 1st and 3rd | Nicole, Emma and student volunteers | This volunteer service will be completed by graduate student volunteers who are already identified and committed to the project
Garden Design and Planting | Phase 2 planting implementation | October | October 4th and 5th | Nicole, Emma and student volunteers
Garden Design and Planting | Planting maintenance schedule | October-March | Seasonal, as needed | Nicole, Emma and student volunteers
Garden Design and Planting | Native seed harvesting workshop | November | late October-early November | Nicole, Emma and student volunteers | Workshop leader TBD; student volunteers harvest, clean and store native seeds for spring planting
Rainwater Sculpture | Organize and implement rainwater sculptural maintenance | Fall, Winter and Spring quarters | October-April | Nicole, Emma and student volunteers
Winter quarter
Garden Design and Planting, Rainwater sculpture | Develop Phase 3 planting design, native perennials from seed, succession planting, seed tray design | Winter quarter | January | Nicole, Emma and student volunteers
| Build Phase 3 seed trays | Winter quarter | February | "
| Phase 3 planting, native annuals and perennials from nursery | Winter quarter | March | "
| Phase 3 planting, growing native annuals and perennials from harvested seed | Winter quarter | March | "
| Fall/winter planting and sculpture maintenance continues through March and April | Winter, Spring quarters | March/April | "
| Initiate process to make CDB courtyard available to students | Winter quarter | March | Nicole, Emma and Jim | Begin coordinating with UW stakeholders to add the CDB courtyard to campus-wide and/or college-wide event space database
| Planting maintenance schedule | Winter quarter | March | Nicole, Emma and student volunters
Spring quarter
Garden Design and Planting, Rainwater sculpture | Phase 4 planting, planting out native seedlings | Spring quarter | March, April | Nicole, Emma, student volunteers
| Advertise CDB courtyard as available for student events | Spring quarter | Timing tbd based on UW stakeholder feedback | Nicole, Emma, Jim
| Assess rainwater sculpture for functionality and propose repairs/updates as needed | Spring quarter | March | Nicole, Emma, Jim
| Begin designing pollinator surveys and recruiting student volunteers | Spring quarter | March | Nicole, Emma, UW stakeholders | Potential for partnerships with student groups, Burke Meadow etc
| Begin recruiting/training for summer garden maintenance | Spring quarter | March-May | Nicole, Emma
| Begin transitioning admin structure from paid position to volunteer | Spring quarter | May | Nicole, Emma

## Timeline Template 2
Implementation Timeline Template 2
Project Name:
Project Element | Task | Owner | Notes | Deadlines (quarter based)
|  |  |  | Summer 24 | Autumn 24 W3 | Autumn 24 W7 | Winter 25 W4 | Winter 25 W8 | Spring 25 W1 | Summer 25
| Retrofit Permissions | Fotima
| Design Plan | Kyle
PACCAR Skybridge | Installation | Yahia
| Monitoring Begins | Rasheena
| Live Bird Screens | Gulsima

## Timeline Template 3
Implementation Timeline Template 3
Project Name:
Project Element | Task | Sub Task | Owner | Notes | 2024 | [11 empty] | 2025
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Design | Blueprint | Boe | bar: 2024 Jan
| Implementation | Ground prep | Tatiana | bar: 2024 March
Storage Facility |  | Purchase materials | Kort | bar: 2024 June
|  | Construction | Danny | bar: 2024 June