## Timeline
Implementation Timeline
Project Name: | UW Native Food Ecosystem
Project Element | Task | Sub Task | Owner | Notes | 2026 | [11 empty] | 2027
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
Burke Meadow | Plant Monitoring | Data Collection | student team | all work collaborative
|  | Data Analysis | student team | all work collaborative | bar: 2026 March; 2026 June; 2026 Sept; 2026 Dec; 2027 March; 2027 June; 2027 Sept; 2027 Dec
|  | Data Presentation | student team | all work collaborative | bar: 2026 May; 2026 Nov; 2027 May; 2027 Nov
| Meadow Work Party | Weeding | student/faculty/staff | all work collaborative | bar: 2026 March to 2026 June; 2026 Sept to 2026 Nov; 2027 March to 2027 June; 2027 Sept to 2027 Nov
|  | Planting | student/faculty/staff | all work collaborative | bar: 2026 Jan to 2026 Feb; 2026 Nov; 2027 Jan to 2027 Feb; 2027 Nov
| Workshop | Basket Weaving | student/faculty/staff | all work collaborative | bar: 2026 Feb to 2026 March; 2027 Feb to 2027 March
|  | Seed Collection | student team | all work collaborative | bar: 2026 June to 2026 Sept; 2027 June to 2027 Sept
| Team Meetings | Weekly Check-In | student/faculty/staff | all work collaborative | bar: 2026 Jan to 2026 June; 2026 Sept to 2027 June; 2027 Sept to 2027 Dec
| Commuinications | Public/Internal | student team | all work collaborative | bar: 2026 Jan to 2026 June; 2026 Sept to 2027 June; 2027 Sept to 2027 Dec
student team
Advisory Board | Meetings | Advisory | All | bar: 2026 Jan; 2026 March; 2026 June; 2026 Sept; 2026 Nov; 2027 Jan; 2027 March; 2027 June; 2027 Sept; 2027 Nov
|  | Commuinications | student team | bar: 2026 Feb; 2026 May; 2026 Aug; 2026 Oct; 2026 Dec; 2027 Feb; 2027 May; 2027 Aug; 2027 Oct
Intermittent Activities | Activities such as UW course discussions, public/academic presentations, and events happen through out the calendar year and are scheduled accordingly