## Timeline Template 1
Implementation Timeline Template 1 |  |  | Feel free to use our template, edit this to fit your timeline needs, or create a new version. We also welcome clear handwritten drawnings. There are a few more templates on the subsequent sheets.
Project Name: | Obtaining Medical Interpreter Certifications for Harborview Translator Program Volunteers
Project Milestone | Tasks | Timeframe | Estimated Completion Date | Owner | Notes
| Brainstorm | March-May | 2024-05-30 | Boe
| Draft questions | May | 2024-05-31 | Tatiana
Interview Guide | Focus group feedback | June | 2024-06-30 | Kort
| Version 2.0 | July | 2024-07-31 | Danny

## Timeline Template 2
Implementation Timeline Template 2
Project Name:
Project Element | Task | Owner | Notes | Deadlines (quarter based)
|  |  |  | Summer 24 | Autumn 24 W3 | Autumn 24 W7 | Winter 25 W4 | Winter 25 W8 | Spring 25 W1 | Summer 25
| Retrofit Permissions | Fotima
| Design Plan | Kyle
PACCAR Skybridge | Installation | Yahia
| Monitoring Begins | Rasheena
| Live Bird Screens | Gulsima

## Timeline Template 3
Implementation Timeline
Project Name: | Obtaining Medical Interpreter Certifications for Harborview Translator Program Volunteers
Project Element | Task | Sub Task | Owner | Notes | 2025 | [11 empty] | 2026
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Brainstorm | Identify Exam | Olivia | bar: 2025 Aug to 2025 Sept
| Confirm Partners | SPH Fiscal Admin | Olivia | bar: 2025 Oct
Grant Proposal |  | Harborview | Anna | bar: 2025 Sept
| Submit Proposal |  | Olivia | bar: 2025 Oct to 2025 Dec
Ram | bar: 2025 Oct to 2025 Dec
| Identify Eligible Volunteers | Confirm Participation | Anna | bar: 2026 Jan to 2026 Feb
|  | Create Group Slack/Email chain | Amber | bar: 2026 Jan to 2026 Feb
Volunteer Outreach | Order Exams | Confirm Test Dates | Olivia | bar: 2026 Feb to 2026 March
Ram | bar: 2026 Feb to 2026 March
| Conduct Outreach with Additional Hospitals/Clinics |  | Emily | bar: 2026 Jan to 2026 March
Ram | bar: 2026 Jan to 2026 March
| Organize Group Study Sessions | Reserve Study Room (Odegaard 22) | Olivia | bar: 2026 Feb to 2026 June
| Confirm Transportation Needs | Use Slack/Email | Anna | bar: 2026 April to 2026 May
Exam Preparation | Ensure Exam Preparation | Remind 1 week in advance | Amber | bar: 2026 June
|  | Remind 1 day before | Amber | bar: 2026 June
| Take Exam | Transport Volunteers | Anna, Amber, Olivia | bar: 2026 June
| Project Leads Meet | Survey Volunteers | Amber | bar: 2026 July to 2026 Aug
|  | Count Successful Certifications | Olivia | bar: 2026 July to 2026 Aug
Reflections |  | Discuss Efficacy with Harborview | Anna | bar: 2026 July to 2026 Aug
|  | Develop Insights for Future | Full Team | bar: 2026 July to 2026 Aug