## Timeline Template 3
Implementation Timeline Template 3
Project Name: | Ultra-Low Temperature Freezer Optimization Through Sensor Monitoring
Project Element | Task | Owner | Notes | 2026 | [10 empty] | 2027
|  |  |  | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb
Project Planning & Coordination | Conduct project kickoff meeting with UW stakeholders | Project Manager | Facilities, Sustainability, Green Labs | bar: 2026 Feb
| Recruit participating laboratories and secure agreements | Project Manager | 20–30 ULT freezers | bar: 2026 Feb to 2026 March
| Assign student roles and responsibilities | Project Manager | PM, Technical, Data, Outreach | bar: 2026 Feb
| Complete electrical and lab safety training | Project Manager | EH&S coordination | bar: 2026 Feb to 2026 March
| Finalize project scope and objectives | Project Manager | Faculty mentor oversight | bar: 2026 Feb to 2026 March
Instrumentation & Setup | Identify representative sample of ULT freezers | Technical Lead | Cross-departmental selection | bar: 2026 March
| Purchase temperature and energy sensors | Technical Lead | Vendor coordination | bar: 2026 March
| Create plans for the installation of the sensors | Technical Lead | Minimize disruption to research | bar: 2026 March to 2026 April
| Prepare the data collection protocols under the supervision of Alexander Mamishev | Technical Lead | Protocols finalized prior to installs | bar: 2026 April
| Arrange for licensed electricians to install energy monitoring equipment | Project Manager | Panel/receptacle work as required | bar: 2026 April
Baseline Monitoring | Arrange for the installation of temperature sensors in the designated ULT freezers | Technical Lead | Coordinate with laboratory personnel | bar: 2026 April
| Begin the collection of baseline performance data from the freezers | Data Analyst | Baseline period begins after installs | bar: 2026 April
| Conduct quality assurance tests to verify that all sensors are functioning properly and transmitting accurate data | Data Analyst | QA/QC following installation | bar: 2026 April to 2026 June
| Collect baseline performance data from the freezers during the normal operating conditions (prior to any scheduled maintenance) | Data Analyst | Baseline dataset prior to interventions | bar: 2026 April to 2026 June
| Provide regular updates to the laboratory users regarding the status of the project | Outreach Coordinator | Encourage open communication | bar: 2026 May to 2026 June
Preventive Maintenance Interventions | Convene a meeting with the participating laboratory representatives and UW Facilities personnel to discuss the preliminary findings | Project Manager | Mid-project progress check | bar: 2026 July
| Organize preventive maintenance on a portion of the monitored freezers (e.g., cleaning condenser coils or inspecting door seals) | Project Manager | Conducted in conjunction with UW Facilities | bar: 2026 July
| Log the maintenance activities and capture pre- and post-maintenance data | Data Analyst | Maintenance actions time-stamped | bar: 2026 July to 2026 Aug
| Track any variations in energy consumption or temperature stability post-maintenance | Data Analyst | Capture improvements and anomalies | bar: 2026 July to 2026 Aug
| Communicate with the laboratory personnel regarding the project’s status and any significant observations | Outreach Coordinator | Plain-language lab updates | bar: 2026 Aug
Post-Maintenance Monitoring & Analysis | Continue to monitor the freezers intensively to collect post-maintenance performance data and compare it to the previous baseline metrics | Data Analyst | Post-maintenance monitoring period | bar: 2026 Aug to 2026 Oct
| Resolve sensor or equipment problems (e.g., sensor failure or data gap) using available backup sensors or technical assistance | Technical Lead | Mitigate disruption risk | bar: 2026 Aug to 2026 Sept
| Review the dataset comprehensively and conduct preliminary comparative analysis | Data Analyst | Maintained vs non-maintained comparison | bar: 2026 Sept to 2026 Nov
| Download and safeguard all the data, back it up, and conduct final validation checks | Data Analyst | Dataset finalized for analysis | bar: 2026 Oct to 2026 Dec
| Conduct in-depth analysis correlating temperature profiles and energy consumption trends with the maintenance events for each freezer | Data Analyst | Statistical tools; mentor guidance | bar: 2026 Nov to 2026 Dec
Reporting, Outreach & Project Closeout | Initiate drafting the framework of a business case for wider implementation of ULT freezer maintenance programs based upon the data-driven findings | Project Manager | Campus adoption rationale | bar: 2026 Nov to 2026 Dec
| Create a strong and compelling business case for implementing free or low-cost preventive maintenance for ULT freezers across the entire campus | Project Manager | Supported by quantified savings | bar: 2026 Nov to 2026 Dec
| Translate the technical findings into accessible formats such as educational materials (e.g., infographics, summary reports, presentation slides) | Outreach Coordinator | Materials for labs and campus units | bar: 2026 Dec to 2027 Jan
| Present the project findings and recommendations to the UW Facilities Management, UW Sustainability Office, and other key stakeholders | Student Team | Formal stakeholder briefing | bar: 2026 Dec to 2027 Jan
| Host a workshop or campus seminar presenting the project findings to the larger UW community | Outreach Coordinator | Education + behavior change | bar: 2027 Jan