## Timeline Template 1
Implementation Timeline Template 1 |  |  | Feel free to use our template, edit this to fit your timeline needs, or create a new version. We also welcome clear handwritten drawnings. There are a few more templates on the subsequent sheets.
Project Name: | JSA Matsuri
Project Milestone | Tasks | Timeframe | Estimated Completion Date | Owner | Notes
| Theme Brainstorm | Sep - Oct | 2025-12-30 | Tomo
Fall | Food menu | Oct- Dec | 12/15/2025 | Sakura
| Games | Oct -Dec | 2025-12-30 | Jarrett
| Performance Contact | Oct- Dec | 2025-12-30 | Akari
| Order products needed for each team | Jan - Feb | 2/15/2026 | Miyu
| Marketing Design | Jan -March | 3/15/2026 | Kyle
Winter | Finalize Performers | Jan-March | 3/15/2026 | Akari
| Volunteers singups | Feb - April | 4/15/2026 | Sofia
| Finalize Deco | Frb - April | 2026-04-15 | Sydney
| Finalize Games | Feb - April | 2026-04-15 | Jarrett
Spring | Event day | May | 2026-05-09 | Tomo

## Timeline Template 2
Implementation Timeline Template 2
Project Name:
Project Element | Task | Owner | Notes | Deadlines (quarter based)
|  |  |  | Summer 24 | Autumn 24 W3 | Autumn 24 W7 | Winter 25 W4 | Winter 25 W8 | Spring 25 W1 | Summer 25
| Retrofit Permissions | Fotima
| Design Plan | Kyle
PACCAR Skybridge | Installation | Yahia
| Monitoring Begins | Rasheena
| Live Bird Screens | Gulsima

## Timeline Template 3
Implementation Timeline Template 3
Project Name:
Project Element | Task | Sub Task | Owner | Notes | 2024 | [11 empty] | 2025
[5 empty] | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Design | Blueprint | Boe | bar: 2024 Jan
| Implementation | Ground prep | Tatiana | bar: 2024 March
Storage Facility |  | Purchase materials | Kort | bar: 2024 June
|  | Construction | Danny | bar: 2024 June