## Budget
Project Budget | Autumn 2024 | Winter 2025 | Spring 2025 | Summer 2023** | Autumn 20232 | Winter 2024
Lead: Judy Bowes (Volunteer) | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits (Graduate Student) | 0% | 0% | 0% | 0% | 0% | 0%
Total Graduate Wages (up to 10 hours a week each at $22 an hour) | 0 | 0 | 0 | 0 | 0 | 0
Erik Rayas – Bird Friendly Designer and Consultant (Architecture Major) | 2200 | 2200 | 2200 | 0 | 0 | 0
Summer Delahanty – App and Bird Friendly Patterns Designer (Human Centered Design Major) | 2200 | 2200 | 2200 | 0 | 0 | 0
Kenna Daily – Field Research Lead (Environmental Studies Major) | 2200 | 2200 | 2200 | 0 | 0 | 0
Parshvi Balu – Lead App Developer (Informatics Major) | 2200 | 2200 | 2200 | 0 | 0 | 0
Total Before Fringe | 8800 | 8800 | 8800 | 0 | 0 | 0
Fringe Benefits (Hourly) | 21.6% | 23% | 23% | 0% | 0% | 0%
Total Hourly Wages | 10700.8 | 10824 | 10824 | 0 | 0 | 0 | 32348.8
| 10700.8 | 10824 | 10824 | 0 | 0 | 0 | 32348.8
Total Wages | 32348.8
Bird Friendly Retrofitting Patterns and Signage* | 30000
Monitoring Supplies (Total for all quarters) | 650
Phase 2 Total | 62998.8
*We are open to compagning for funding in the community.

## Timeline
Deadlines
| Task | Autumn Week 5 | Autumn Week 10 | Winter Week 5 | Winter Week 10 | Spring Week 5 | Spring Week 10
Site 1 (PACCAR Walkways)
Retrofit Permissions |  | x
Design Plan |  | x
Installation |  |  | x
APP | Live Bird Screens | Testing Begins | x
Site 2 (Forest Lab)
Retrofit Permissions |  |  |  | x
Design Plan |  |  |  | x
Installation |  |  |  |  | x
APP | Bird Friendly Design Screens |  |  | Testing Begins | x
Site 3 (Pop Health)
Retrofit Permissions |  |  |  |  | x
Design Plan |  |  |  |  | x
Installation | [5 empty] | x
APP | Bird Friendly Filters |  |  |  | Testing Begins | x
Site 4 (TBD)
Retrofit Permissions |  |  |  |  | x
Design Plan |  |  |  |  | x
Installation | [5 empty] | x
APP | Final Testing - Lifetime Set up |  |  |  |  | x
Final Monitoring and Data Analysis | [6 empty] | x