**Hydrogen Jukebox Project Timeline**

|  |  |  |
| --- | --- | --- |
| **Task** | **Start Date** | **Estimated Completion** |
| Production Meeting #1 | December 10, 2018 | December 10, 2018 |
| Production Meeting #2 |  January 14, 2019 |  January 14, 2019 |
| Musical Rehearsals begin | January 7, 2019 | February 3, 2019 |
| Staging & Choreography Rehearsals begin | February 3, 2019 | April 19, 2019 |
| Orchestral Rehearsals begin | January 22, 2019 | April 18, 2019 |
| Sound System confirmation | January 22, 2019 | April 22, 2019 |
| Microphone purchase | January 14, 2019 | February 11, 2019 |
| Costume sizing for cast | March 4, 2019 | March 4, 2019 |
| Costuming and Props | March 6, 2019 | April 16, 2019 |
| Set design confirmation | March 6, 2019 | April 16, 2019 |
| **University Spring Break** | **March 16, 2019** | **April 1, 2019** |
| Lighting design | January 14, 2019 | April 15, 2019 |
| Projector rental Confirmation | January 14, 2019 | February 25, 2019 |
| Projection design | January 14, 2019 | April 22, 2019 |
| Discussion panel: call for membership | ongoing | participation confirmed: February 25, 2019 |
| Discussion panel: preliminary meeting | March 14, 2019 | March 14, 2019 |
| Promotional materials generation | ongoing | March 18, 2019 |
| Promotional materials distribution | March 18, 2019 | April 27, 2019 |
| Lighting Meeting | March 4, 2019 | March 4, 2019 |
| Program Materials Due  |  April 1, 2019 | April 1, 2019 |
| Program Printing | April 22, 2019 | April 22, 2019 |
| Final Room Run #1, Meany 268 | April 17, 2019 | April 17, 2019 |
| Orchestra Sitzprobe, Meany 268 | April 18, 2019 | April 18, 2019 |
| Final Room Run #2, Meany 268 | April 19, 2019 | April 19, 2019 |
| Projector Delivery | April 20, 2019 | April 20, 2019 |
| Meany Studio Load-In | April 22, 2019 | April 22, 2019 |
| Piano Tech Rehearsal | April 22, 2019 | April 22, 2019 |
| Production Tech/Lighting | April 22, 2019 | April 26, 2019 |
| Orchestra Dress Rehearsal #1 | April 23, 2019 | April 23, 2019 |
| Orchestra Dress Rehearsal #2 | April 24, 2019 | April 24, 2019 |
| Performance #1, Discussion Panel | April 26, 2019 | April 26, 2019 |
| Performance #2, Discussion Panel and Set Strike | April 27, 2019 | April 27, 2019 |
| Load out | April 28, 2019 | April 28, 2019 |