## Timeline
SALVAGE WOOD TIMELINE |  |  |  |  | 2024 | [9 empty] | 2025 | [11 empty] | 2026
Project | Task | Sub Tasks | Owner | Notes | March | April | May | June | July | August | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec | Jan | Feb | March | April
Application/Approval Process | LOI due |  | Marlee | 03/01-03/31 | bar: 2024 March
| CSF approval |  | Marlee | 04/01-04/05 | bar: 2024 April
| Full proposal due | Executive summary | Marlee | Each section has several criteria that needs to be addressed (ex: timeline needs to be included in accountability and feasibility section) full proposal due 05/05 | bar: 2024 May
|  | Funding and budget Info | Marlee | bar: 2024 May
|  | Sustainability impact | Marlee | bar: 2024 May
|  | Education and outreach | Marlee | bar: 2024 May
|  | Student involvment | Marlee | bar: 2024 May
|  | Accountability and feasibility | Marlee | bar: 2024 May
|  | Partners and stakeholders | Marlee | bar: 2024 May
| CSF approval |  | Marlee | End of May | bar: 2024 May
Storage Facility | Design | Blueprint | Rae | bar: 2024 March
|  | UW approval | Rae | bar: 2024 April to 2024 May
| Implementation | Ground preparation | Rae | bar: 2024 April to 2024 May
|  | Purchase materials | Rae | bar: 2024 April to 2024 May
|  | Recruit students | Rae | bar: 2024 April to 2024 May
|  | Construction | Rae | bar: 2024 May to 2024 August
Wood Processing | Planing |  | Morgan | Triannually | bar: 2024 Sept; 2024 Dec; 2025 March; 2025 Sept; 2025 Dec; 2026 March
| Inventory |  | Morgan | Triannually | bar: 2024 Oct; 2025 Jan; 2025 April; 2025 Oct; 2026 Jan; 2026 April
| Hauling |  | Morgan | Triannually | bar: 2024 Oct; 2025 Jan; 2025 April; 2025 Oct; 2026 Jan; 2026 April
| Website Inventory/Asset Management |  | Sara | Annually | bar: 2024 Sept to 2024 Dec; 2025 Sept to 2025 Dec
Wood Usage | Purchased |  | Rae | Triannually | bar: 2024 Sept; 2024 Dec; 2025 March; 2025 Sept; 2025 Dec; 2026 March
| Inventory |  | Rae | Triannually | bar: 2024 Oct; 2025 Jan; 2025 April; 2025 Oct; 2026 Jan; 2026 April
Outreach | Student Involvement | Tour of carpentry shop | Morgan | Triannually | bar: 2024 Oct; 2025 Jan; 2025 April; 2025 Oct; 2026 Jan; 2026 April
| Advertising | Sustainability Fair | Marlee | Annually | bar: 2024 Oct; 2025 Oct
|  | Earth Day Event | Marlee | Annually | bar: 2025 April; 2026 April
|  | Email to students | Marlee | Triannually | bar: 2024 August; 2024 Nov; 2025 Feb; 2025 August; 2025 Nov; 2026 Feb
| Class Final Review Event | Students show off designs | Rae | Triannually | bar: 2024 Dec; 2025 March; 2025 June; 2025 Dec; 2026 March

## Budget
Cost Categories | Grant Expenses Breakdown | Cost Type | Amount ($) | Sub-Total ($) | Notes
Equipment | Shed construction | One-Time | 5000 | 5000 | Includes all materials and labor
Salary Overhead | Planing wood | Triannually | 1000 | 6000 | Estimate to plane 30 boards: 10 minutes/board
| Inventory: FMC | Triannually | 250 | 1500 | Four inventories used in carpentry: logs, green slabs, in kiln, in shop
| Website updates | Annually | 1500 | 3000 | Custom wood orders, cost estimates, create real time system etc.
| Student tours | Triannually | 400 | 2400 | Provides students with an opportunity to visit the carpentry shop, get a tour of the facility, see the kiln and saw mill, see the wood being processed, etc.; 2.5 hrs per quarter at the caprenter rate
| Hauling | Triannually | 400 | 2400 | 2.5 hrs per quarter at the heavy equipment change rate to transfer wood
Supplies | Board purchase | Triannually | 6400 | 38400 | First two years CSF funds will purchase wood for student use. Once the program is fully implemented and streamlined, the college will purchase wood.
TOTAL REQUEST: CSF |  |  |  | 58700